## PB Canvas
If you need to understand more about the Value Proposition Canvas and how to fill this TAB :https://www.youtube.com/watch?v=aN36EcTE54Q&
Name of the Product/Service:
Give a name to you product or service...
Short Description:
Short Description about the project.
| Pains | Expected Gains | Job to Be Done | Features (Provided Gains and Pain Relievers)
Persona1: | Access content of the classes in three different places |  |  | F1- INtegration of links of contents from different systems in one page
|  | Informed by SMS about the Exams | Study | F2 -Implement a SMS component
Persona2:
PersonaN

## PB Items
Product Backlog Template
|  | Persona(who) | Action(What) | Value(Why)
ID | Feature ID | As a..... | I want to be able to... | So that... | Priority(MoSCoW) | Sprint-ID | Status | Tasks/ Owner | Estimation | Acceptance Criteria
US1 | F1 | customer | select different comics from a list | ..I can buy them | Must Have | 1 |  | Task1, Task2....Taskn | See Categories | User sees a list of different comics and can select one to see it in a single view
US2 | F2 | customer | create an account | ..I can pay online | Must Have | 2 |  |  |  | User can deposit his name, an Email-Address, and a Paypal-Account
US3 | F3 | salesman | add new comics | ..I can sell them | Must Have | 3 |  |  |  | User can create new comic-objects
US4 | F4 | writer | add announcements | ..they are advertisement | Could Have | 4 |  |  |  | User can create special announcement-objects
US5 | F5 | salesman | create a newsletter | ..I can give it to users | Could Have | 5 |  |  |  | User can save a list of comic-objects and announcement-objects and transfer it to a Email-Address
US6 | F6 | customer | search for keywords | ..I can find comics and their authors | Could Have | 6 |  |  |  | User sees a search bar
US7
US8
US9
US10
US11

## Categories
Status
Done, Work in Progress, To be Started
Estimation
Fibonacci Series | https://www.visual-paradigm.com/scrum/what-is-story-point-in-agile/#:~:text=While%20estimating%20story%20points%2C%20we,is%20estimated%203%20story%20points.
https://jexo.io/blog/guide-to-understanding-story-points/
Priority - MoSCoW
https://en.wikipedia.org/wiki/MoSCoW_method
Must have
Requirements labelled as Must have are critical to the current delivery timebox in order for it to be a success. If even one Must have requirement is not included, the project delivery should be considered a failure (note: requirements can be downgraded from Must have, by agreement with all relevant stakeholders; for example, when new requirements are deemed more important). MUST can also be considered an acronym for the Minimum Usable Subset.
Should have
Requirements labelled as Should have are important but not necessary for delivery in the current delivery timebox. While Should have requirements can be as important as Must have, they are often not as time-critical or there may be another way to satisfy the requirement so that it can be held back until a future delivery timebox.
Could have
Requirements labelled as Could have are desirable but not necessary and could improve the user experience or customer satisfaction for a little development cost. These will typically be included if time and resources permit.
Won't have (this time)
Requirements labelled as Won't have, have been agreed by stakeholders as the least-critical, lowest-payback items, or not appropriate at that time. As a result, Won't have requirements are not planned into the schedule for the next delivery timebox. Won't have requirements are either dropped or reconsidered for inclusion in a later timebox. (Note: occasionally the term Would like to have is used; however, that usage is incorrect, as this last priority is clearly stating something is outside the scope of delivery). (The BCS in edition 3 & 4 of the Business Analysis Book describe 'W' as 'Want to have but not this time around')